## Sheet1
Group 9 Product Backlog
User Story ID | User | I want to be able to... | So that I can... | Priority | Risk/Value | Points | Status
1 | Site Visitor | Select a development goal | See more information about it | Must | Low/High | 3 | Done
2 | Site Visitor | See development goals that are in Dundee | Contribute to goals in Dundee | Should | Low/High | 3 | Done
3 | Site Visitor | Select an event | See more detailed information about that event (contact details, event info etc.) | Must | Low/Low | 2 | Done
4 | User | Create a personalised list of items | Save them for later use | Could | High/High | 5 | Done
5 | Site Visitor | View the web app on a mobile device | View it on the go or without the use of a computer | Should | High/High | 1 | Done
6 | Site Visitor | Use my current location to see nearby events | Participate in nearby events so that I can participate in events close to me | Could | High/High | ? | Done
7 | Site Visitor | Intergrate with my social media | Check into a location through my social media feed | Could | Low/Low | 1 | Done
8 | Back-End User | Create new items | Add new events onto the website | Must | Low/High | 5 | Done
9 | Back-End User | Edit current events | Update information about them to keep it accurate and up to date | Should | Low/Low | 3 | Done
10 | Back-End User | Remove items | Maintain the website | Must | Low/Low | 2 | Done
11 | Back-End Admin | Select which accounts have add/edit/remove privileges | Help maintain the website and its items | Must | High/High | 13 | Done
13 | Site Visitor | Submit suggestions for events to include on the website | Bring more awareness to an upcoming event | Could | Low/High | 1 | Done
14 | Back-End User | Create tours of events | Other users can easily see where all the goals will be taking place | Could | High/Low | 3 | Done
15 | User | Check into venues and see a leaderboard of other users check ins | Compare my commitment to a goal to other users | Could | High/Low | ? | Not Done
24 | Site Visitor | Access a map of events that are related to a goal that I am interested in | See which events are in my area | Must | High/High | 13 | Done