## Sheet1
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Sprint 1 | User Story #11: Select which accounts can add/edit/remove items | [12 empty] | User Story #8: Allow certain users to create new events |  |  |  |  | User Story #2: See goals In Dundee |  |  | User Story #1: Select goals to see more info |  |  | User Story #3: Select event for more info |  | User Story #9: Allow back end editting of events
Member(s) assigned to story | Khaelem Watt and Struan Robertson (Development Team) | [12 empty] | Elliot Stevenson (Product Owner) |  |  |  |  | Jack Morrison and Antonis Tziouliou (Development Team) | [5 empty] | Archie Milne (Scrum Master)
Progress
Progress Description | Account creation is fully completed, just need to link up the add/edit/remove once logged in | [12 empty] | Creation Page is up and users can input info however it does not get pushed into table |  |  |  |  | All Pages goal pages have been made, pages just need css, images and other pages linked correctly | [5 empty] | All Pages have been made testing still need to be preformed